## Sheet1
Vaccination Scheduling System Exercise 5
Task ID | Task Name | Predecessors | Duration | ES in Start | EF in Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
T1 | Requirements and Model Review | — | 3 | 1 | 3 | bar: 1 to 3
T2 | Development Environment and Database Setup | T1 | 2 | 4 | 5 | bar: 4 to 5
T3 | Database Schema Design | T2 | 3 | 6 | 8 | bar: 6 to 8
T4 | Vaccine Reference Data Setup | T3 | 2 | 9 | 10 | bar: 9 to 10
T5 | Patient Interface Design | T1 | 3 | 4 | 6 | bar: 4 to 6
T6 | Nurse and Staff Interface Design | T1 | 3 | 4 | 6 | bar: 4 to 6
T7 | Authentication and Role Management | T3 | 5 | 9 | 13 | bar: 9 to 13
T8 | Appointment and Waitlist Module | T4, T5, T7 | 8 | 14 | 21 | bar: 14 to 21
T9 | Eligibility and Dose Administration Module | T4, T6, T7 | 7 | 14 | 20 | bar: 14 to 20
T10 | Overdue Flagging Orchestration | T4, T9 | 6 | 21 | 26 | bar: 21 to 26
T11 | Reminders and Notifications | T8, T10 | 5 | 27 | 31 | bar: 27 to 31
T12 | Dashboard, History and Reports | T8, T9 | 6 | 22 | 27 | bar: 22 to 26
T13 | System Integration | T10, T11, T12 | 4 | 32 | 35 | bar: 32 to 35
T14 | Testing | T13 | 6 | 36 | 41 | bar: 36 to 41
T15 | Deployment Preparation and User Guide | T14 | 3 | 42 | 44 | bar: 1; 42 to 44